## T-Shirt Size
| Small |  |  |  | Med |  |  |  | Large |  |  |  | JT/SB Review | JW review | SOW
| PM | App Cons | Sys Cons | Tech Cons | PM | App Cons | Sys Cons | Tech Cons | PM | App Cons | Sys Cons | Tech Cons |  |  | Disclaimer/Terms needed? (Y/N) | HRS Sign Off | Define
Core SO | [17 empty] | Customer Questions
SO Net New - Cloud Services (no -add on modules) | 8 | 44 | 16 | 0 | 35 | 68 | 16 | 0 | 60 | 68 | 16 | 0 |  |  | Yes |  | Small - no conversion, Med - Conversion, Multiple Branches and Under Two Locations Large - > 2 Locations, Multiple Branches or Databases and Conversion
SO Net New - On Prem (no -add on modules) | 8 | 44 | 24 | 0 | 35 | 68 | 24 | 0 | 60 | 68 | 32 | 0 |  |  | Yes |  | Small - no conversion, only AR functions being utilized; Med - Conversion, Multiple Branches and Under Two Locations Large - > 2 Locations, Multiple Branches or Databases and Conversion
Net New Conversion | 10 | 0 | 0 | 24 | 30 | 0 | 0 | 90 | 50 | 0 | 0 | 160 |  |  |  |  | Small - customer extracts data from existing systems, customer fills in staging doc and Bold scripts in SO for up to 3 data passes Med - customer extracts data from existing systems, Bold scripts in staging doc and Bold scripts in SO for up to 3 data passes Large - Bold extracts data from existing systems, customer fills in staging doc and Bold scripts in SO for up to 4+ data passes
Dashboard | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 |  |  | Yes |  | Small - Install Application
Forte Integration (EFT) | 1 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 4 | 2 | 0 | 12 |  |  | Yes |  | Small - existing Forte, new merchant account Med - net new to Forte, Large - net new to Forte and transfer of tokens
ADI Integration | 1 | 3 | 2 | 0 | 1 | 3 | 2 | 0 | 1 | 3 | 2 | 0 |  |  | Yes |  | S,M,L - Net New ADI Integration
WeSuite Integration | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 |  |  | Yes |  | S,M,L - Net New WeSuite Integration
Sebis Integration | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 |  |  | Yes |  | S,M,L - Net New Sebis
SO Modules* | [16 empty] | *Assumes all modules pick up API and upgrade hours when needed
Sedona X Mobile - Net New | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 4 | 4 | 2 | 0 |  |  | Yes |  | Small - license adds only, Med - net new user 1 location, Large -
Sedona-X Mobile App - FSU Migration | [14 empty] | Yes
SalesAutomation | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 2 | 4 | 0 | 0 |  |  | Yes |  | Small - license only, Med - new addon
eForms | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 2 | 5 | 0 | 0 |  |  | Yes |  | Small - license only, Med - new addon
Time and Attendance | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 2 | 4 | 0 | 0 |  |  | Yes |  | Small - license only, Med - new addon
SedonaWeb 2.0 | 1 | 2 | 1 | 0 | 2 | 3 | 1 | 0 | 2 | 3 | 1 | 0 |  |  | Yes |  | Small - net new, no API 2.0 installed Medium - migration and/or needs training
API 2.0 - Full Version | 1 | 0 | 4 | 0 | 2 | 0 | 6 | 0 | 2 | 0 | 6 | 0 |  |  | Yes |  | Small - limited and hosted, medium - on prem
API 2.0 - Limited Version | 1 | 0 | 4 | 0 | 1 | 0 | 4 | 0 | 1 | 0 | 4 | 0
Sedona Sync | 4 | 10 | 6 | 0 | 4 | 16 | 6 | 0 | 4 | 20 | 6 | 0 |  |  | Yes |  | Small - 1 instance, 4 events activated, basic training, medium - multiple branches or databases, 4+ events activated (charge per activation of event), Large - Activation of servnice notifications, multiple db and branches, multiple db connections
FireNSpec | 1 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 1 | 0 |  |  | No |  | Small - 1 database, API 2.0 installed, Secret Code
SO-Manitou Integration | 3 | 3 | 8 | 0 | 3 | 3 | 8 | 0 | 3 | 3 | 8 | 0 |  |  | Yes |  | NOTE: Even if integration is included for free on certain versions, we need to pick the product so that the labor hours come over
SO - Stages Integration | 3 | 3 | 8 | 0 | 3 | 3 | 8 | 0 | 3 | 3 | 8 | 0 |  |  | Yes
SO - CMS Integration | 3 | 3 | 8 | 0 | 3 | 3 | 8 | 0 | 3 | 3 | 8 | 0 |  |  | Yes
SedonaDocs | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 |  |  | No |  | Small - Application takes 30 seconds to activate then apply updated license key
QuoteWorks Integration | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 2 | 0 |  |  | Yes |  | Small: License Add, Med: License Add, Integration Activation, QuoteValet Add
Services | [14 empty] | Yes
BPA - Comprehensive/Focused | 6 | 30 | 0 | 30 | 10 | 62 | 0 | 62 | 20 | 80 | 0 | 80 |  |  | Yes | Yes | Small - Focused BPS Medium - Comprehensive BPA Large - Multiple Companies, Comprehensive BPA
Cloud Migrations | 4 | 1 | 10 | 0 | 4 | 1 | 14 | 0 | 12 | 1 | 28 | 0 |  |  | Yes |  | Need Calculator - Varies on modules, integrations, third party vendors and database size (Justin created working with IT already) Small - Only SedonaOffice and SedonaDocs, Medium- SedonaOffice, SedonaSync, SedonaWeb, or API and Forte Integration, Large - SedonaOffice, SedonaSync, SedonaWeb, or API and Forte Integration, WeSuite Integration, OPT and/or Vivid
Upgrades | 4 | 0 | 8 | 0 | 8 | 4 | 12 | 0 | 8 | 4 | 18 | 0 |  |  | Yes |  | Med - no add on modules or integrations, Large - includes modules and/or integrations
Acqusition Migrations | 6 | 0 | 0 | 30 | 12 | 8 | 0 | 30 | 12 | 8 | 0 | 30 |  |  | Yes | Yes | Small - New Branch Setup in Master Database, 1 Data Source Medium - New Branch Setup in Master Database, 2 - 3 Data Source Large - New Branch Setup in Master Database, 4+ Data Source, Merging data with existing branch
Test Upgrade | 2 | 0 | 8 | 0 | 8 | 8 | 12 | 0 | 8 | 8 | 12 | 0 |  |  | No |  | Small - no add on modules or integrations, Med - includes modules and/or integrations, Large
Forte Token Import (same for MG) | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 8 | 1 | 0 | 0 | 8 |  |  | Yes | Yes | Small - Forte migration, 1 MID Medium - Forte Migration, Multiple Mids
Reinstall | 4 | 0 | 8 | 0 | 8 | 0 | 16 | 0 | 8 | 0 | 16 | 0 |  |  | Yes |  | Small - Only SedonaOffice, SedonaDocs no additional modules, Med - Add-on modules
Managely | [14 empty] | Yes
Net New Managely | 4 | 8 | 0 | 0 | 8 | 16 | 0 | 0 | 12 | 24 | 0 | 0 |  |  | Yes |  | Small - Only using AR, AP or GL Medium - Using GL, Multiple Branches Setup Large - Using GL, Multiple Branches Setup, Enterprise
Managely Conversion | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 40 |  |  |  |  | Small - customer extracts data from existing systems, customer fills in staging doc and Bold scripts in Managely for up to 2 data passes Med - customer extracts data from existing systems, Bold scripts in staging doc and Bold scripts in Managely for up to 2 data passes Large - Bold extracts data from existing systems, customer fills in staging doc and Bold scripts in Managely for up to 3 data passes
AB > Managely | 2 | 7 | 0 | 6 | 8 | 12 | 0 | 6 | 12 | 17 | 0 | 12 |  |  | Yes |  | Small - 1 Source of AB, no additional data outside AB, not using AB GL Med - Conversion, 1 Source of AB, Need GL configured in Mangely Large - Conversion, Up to 2 sources of data or 2 AlarmBilller Databases , Go-Live Resource
SO > Managely | [14 empty] | Yes |  | Never been done, need in
Sedona X | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 0 | 0 |  |  | No |  | Small - License adds only, Med - Net New w/ Training
Core Manitou
On Prem Manitou Lite
On Prem - Standard Bundle | 5 | 8 | 16 | 0 | 5 | 8 | 16 | 0 | 5 | 8 | 16 | 0 |  | yes
On Prem - Business Bundle | 10 | 16 | 40 | 0 | 10 | 16 | 40 | 0 | 10 | 16 | 40 | 0 |  | yes
On Prem - Premier Bundle | 15 | 24 | 80 | 0 | 15 | 24 | 80 | 0 | 15 | 24 | 80 | 0 |  | yes
On Prem - Enterprise Bundle | 20 | 40 | 120 | 0 | 20 | 40 | 120 | 0 | 20 | 40 | 120 | 0 |  | yes
Conversion (Tech Consulting) | 8 | 0 | 0 | 50 | 16 | 0 | 0 | 80 | 24 | 0 | 0 | 120 |  | yes
MCS - Standard Bundle | 5 | 8 | 16 | 0 | 10 | 8 | 16 | 0 | 10 | 8 | 16 | 0 |  | yes
MCS - Business Bundle | 10 | 16 | 40 | 0 | 10 | 16 | 40 | 0 | 10 | 16 | 40 | 0 |  | yes
MCS - Premier Bundle | 15 | 24 | 80 | 0 | 15 | 24 | 80 | 0 | 15 | 24 | 80 | 0 |  | yes
MCS - Enterprise Bundle | 20 | 40 | 120 | 0 | 20 | 40 | 120 | 0 | 20 | 40 | 120 | 0 |  | yes
MCS - PaaS | 3 | 0 | 16 | 0 | 3 | 0 | 16 | 0 | 3 | 0 | 16 | 0 |  | yes
Reinstall | 1 | 0 | 8 | 0 | 1 | 0 | 8 | 0 | 1 | 0 | 8 | 0 |  | yes
Manitou Modules
Universal Connector | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | Yes | yes | Yes |  | Small - comes with exisiting data maps library or custom data map required. Can be a required component for a video driver or added to an integration offering as the receiver.
PBX Telephony (There is no part with this name)
Standard Import Utility | 1 | 4 | 4 | 0 | 1 | 4 | 4 | 0 | 1 | 4 | 4 | 0 | Yes | yes |  |  | Small - Training is required and charged separately
Autotext | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | Yes | yes | Yes |  | Small - Training and installation is required and charged separately. Requires SMS plan from integrated SMS provider.
OpenVoice Inbound | 1 | 2 | 16 | 0 | 1 | 2 | 16 | 0 | 1 | 2 | 16 | 0 | Yes | yes | Yes |  | Med - Requires integration to Tadiran Aeonix. Voice for call can be Microsoft voice that comes with MS OS or Wave file
BoldNet Mobile | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 0 | Yes | yes | Yes |  | Small - Requires BoldNet. Unlimited users
BoldNet | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | Yes | yes | Yes |  | Small - Training and installation is required and charged separately. Requires SQL Express (free version) and is installed in a DMZ.
VCC - (Should be Video Driver) | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | Yes | yes | Yes |  | Small to Medium - May require different modules (UniversalConnector, XML Receiver Driver) to receive feeds. Training and Installation is required and charged separately. We should list or provide link to all exisiting video integrations and what is required.
Bold NotifyMe | [14 empty] | Yes
High Availability | [16 empty] | We are no longer selling this and PdM is removing it.
Stealth | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | Yes | yes | Yes |  | Small - Training and installation is required and charged separately. This can be a stand alone product. Requires SQL (Express or Standard Versions with appropriate number of CALs) that we can sell separately.
Advanced Report Writer | 1 | 4 | 4 | 0 | 1 | 4 | 4 | 0 | 1 | 4 | 4 | 0 | Yes | yes | Yes |  | Small - Training and installation is required and charged separately. Custom reports created require this product to added to Manitou. NOT available in MCS offering.
Manitou Cloud Services (not sure what this is) | [16 empty] | This is a whole different group of parts that are bundled together which vary in complexity.
MCS - SaaS | [14 empty] | Yes |  | Med - Bold will start monthly recurring once Manitou is primary servers processing signals.
OpenVoice Outbound | 1 | 2 | 16 | 0 | 1 | 2 | 16 | 0 | 1 | 2 | 16 | 0 | Yes | yes | Yes |  | Med - Requires integration to Tadiran Aeonix. Voice for call can be Microsoft voice that comes with MS OS or Wave file
Business Continuity Services | [14 empty] | Yes |  | Med - Installation and recurring is charged depending on number of accounts. Comes with DSC System IV receiver and additional receivers may be required and billed separately. There is a per daily activation charge of $3,000.
Cloud Receiver | 3 | 0 | 8 | 0 | 3 | 0 | 16 | 0 | 3 | 0 | 24 | 0 | Will create custom questions for this Module |  | Yes |  | Med - Installation is charged separately. Comes with access to (get list of receivers from Shaun) alarm receivers. Requires customer to have contract with OneTel for teleco signaling. Requires VPN provided by Bold Group or CSS.
Cloud Receiver Backup | [14 empty] | Yes |  | Med - Installation is charged separately. Comes with access to (get list of receivers from Shaun) alarm receivers. Requires customer to have contract with OneTel for teleco signaling. Requires VPN provided by Bold Group or CSS. Customer will be billed at a higher rate if Backup becomes Primary.
Virtual Operator | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 0 | Yes | yes |  |  | Small - Installation and training charged separately.
PBX Cloud | 2 | 0 | 16 | 0 | 2 | 0 | 16 | 0 | 2 | 0 | 16 | 0 | Yes | yes | Yes |  | Small - Installation charged separately. Integration available with Total Connect???????????
PBX Standard | 2 | 0 | 16 | 0 | 2 | 0 | 16 | 0 | 2 | 0 | 16 | 0 | Yes | yes | Yes |  | Small - Installation charged separately. Integration available with Tadiran Aeonix
PBX Enterprise | 4 | 0 | 24 | 0 | 4 | 0 | 24 | 0 | 4 | 0 | 24 | 0 | Yes | yes | Yes |  | Med - Installation charged separately. Integration for TwoWayPlus and OpenVoice is sold separately.
Voice Record | 1 | 2 | 8 | 0 | 1 | 2 | 8 | 0 | 1 | 2 | 8 | 0 | Yes | yes | Yes |  | Small - Installation and training charged separately. Intergration ONLY available with SecureVoice
Warm Replication | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | Yes | yes | Yes |  | Med - Installation and training charged separately. SQL (Standard with CALs or Per Core Versions) is sold separately.
Multi Replication | 1 | 2 | 8 | 0 | 1 | 2 | 8 | 0 | 1 | 2 | 8 | 0 | Yes | yes | Yes |  | Med - Installation and training charged separately. Comes with licensing for 3+ instances of Manitou. SQL (Standard with CALs or Per Core Versions) is sold separately.
AccessPoint | 2 | 2 | 16 | 0 | 2 | 2 | 16 | 0 | 2 | 2 | 16 | 0 | Yes | yes | Yes |  | Med - Installation and training charged separately. Integration to specific Access Control (Lenel, Open Options, ask dev for others). May require another Bold product to receive signals.
Location Services | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | Yes | yes | Yes |  | Small - Installation and training charged separately. Product is provided by Intrado. Comes with limit of 500 number of dips to Intrado database and $.25/dip after limit is exceeded.
ASAP to PSAP | 1 | 2 | 8 | 0 | 1 | 2 | 8 | 0 | 1 | 2 | 8 | 0 | Yes | yes | Yes |  | Small - Installation, working with TMA and Training charged separately. Requires customer to work with TMA and specific AHJ.
BoldTrak (1500 or Unlimited) | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | Yes | yes | Yes |  | Small - Installation and training charged separately. Requires BoldNet and other Bold Group receiving component (UniversalConnector, XML Receiver Driver, SDK) to receive signaling.
Dealer Billing | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | Yes | yes |  |  | Small - Installation and training charged separately.
Enhanced Dealer Billing | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | 1 | 2 | 4 | 0 | Yes | yes |  |  | Small - Installation and training charged separately. Requires SedonaOffice to connect to Manitou. SDK is used to connect and we can give it to them for free IF THEY HAVE BoldNet.
Software Developers Kit (MDK) | 1 | 0 | 8 | 0 | 1 | 0 | 8 | 0 | 1 | 0 | 8 | 0 | Yes | yes | Yes |  | Small - Requires BoldNet. Training could be sold separately.
Remote FEP | 1 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | Yes | yes |  |  | Small - Installation charged separately.
SoloProtect | [14 empty] | Yes |  | I'm not sure if we still sell this?
Training Gym Tier 1 | 1 | 1 | 4 | 0 | 1 | 1 | 4 | 0 | 1 | 1 | 4 | 0 | Yes | yes | Yes |  | Small - Installation charged separately. SQL (Express or Standard with appropriate CALs) is sold separately.
Training Gym Tier 2 | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | 1 | 1 | 8 | 0 | Yes | yes | Yes |  | Med - Installation charged separately. SQL (Express or Standard with appropriate CALs) is sold separately.
Training Gym Tier 3 | 1 | 2 | 16 | 0 | 1 | 2 | 16 | 0 | 1 | 2 | 16 | 0 | Yes | yes | Yes |  | Large - Installation charged separately. SQL (Express or Standard with appropriate CALs) is sold separately.
XML Receiver Driver | 1 | 0 | 2 | 0 | 1 | 1 | 4 | 0 | 1 | 4 | 8 | 0 | Survey Question: "Is this for an existing or new integration?" | yes |  |  | Small - Installation charged separately.
Monitoring Group | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 0 | Yes | yes |  |  | Small - Installation and training charged separately.
TwoWayPlus | 1 | 2 | 8 | 0 | 1 | 2 | 16 | 0 | 1 | 2 | 24 | 0 | Yes | yes | Yes |  | Med - Installation and training charged separately. Comes with 4 lines of TwoWay. Required to use with Tadiran Aeonix and PBX Enterprise (sold separately).
TwoWayPlus - InstantConnect | [14 empty] | Yes |  | Med - Installation and training charged separately. Comes with 4 lines of TwoWay. Required to use with Tadiran Aeonix and PBX Enterprise (sold separately).
History Server | 1 | 0 | 4 | 0 | 1 | 0 | 4 | 0 | 1 | 0 | 4 | 0 | Yes | yes
Accounting Integration | 1 | 8 | 8 | 0 | 1 | 8 | 8 | 0 | 1 | 8 | 8 | 0 | Hours could change after integration, check with Rocky. | yes | Yes |  | Small - SQL not included.
Manitou to SedonaOffice | [14 empty] | Yes |  | Small - Installation and training charged separately. Requires SedonaOffice to connect to Manitou. SDK is used to connect and we can give it to them for free IF THEY HAVE BoldNet.
Manitou to AlarmBiller | [16 empty] | I don't know what's needed for this.
SIMS
SIMS Net New | NA | NA | NA | NA | NA | NA | NA | NA | 8 | 16 | 40 | 0
SIMS 3 Receiver | 1 | 1 | 2 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
SIMS 3 for Windows | 1 | 1 | 2 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
Formwriter 3 | 1 | 1 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 4 | 1 | 0 |  |  |  |  | Small - brand new setup with basic reports, Med - 10-20 reports, Large - more than 20 reports
iPocket Server | 1 | 1 | 1 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
Comserver 3 | 1 | 1 | 2 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
SIMS Web 4 (IIS) | 1 | 2 | 4 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
SIMS Dispatch (IIS) | 1 | 2 | 4 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
Upgrade to SQL | 8 | 16 | 24 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
Vapor Paper | 1 | 2 | 2 | 0 | NA | NA | NA | NA | 1 | 2 | 4 | 0 |  |  |  |  | Small (4 port), more than 4 is Large
SIMS Overwatch | 0 | 0 | 1 | 0 | NA | NA | NA | NA | NA | NA | NA | NA
SQL Mirroring | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 1 | 6 | 0
Core Stages
Stages Net New | NA | NA | NA | NA | NA | NA | NA | NA | 160 | 30 | 60 | 20
Stages Conversion | NA | NA | NA | NA | NA | NA | NA | NA | 220 | 50 | 120 | 200
Stages Parts/Modules
Backstage | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | Yes |  | Small - Can be physical 1U server or virtual. Same amount of effort to deploy until a large number of hosts are being monitored .
Network Navigator | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | Yes |  | Hardware product. We need to discuss this since there are other ways to sell this product.
Backstage and Network Nav MCS VPN | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 4 | 0 |  |  | Yes |  | Hardware product and Backstage can be virtual. Required together to meet UL configuration.
stages Connect | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | Yes |  | Hardware product preloaded and configured. Virtual offerning VMWare or Hyper-V
Virtual Communication Center | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 4 | 0 |  |  | Yes |  | Virtual appliances for BSM, Connect, IVR -- unlimited deployments , verify language in contracts.
Chat Service | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | Yes |  | Same effort to deploy Chat S, M, L
SMS Gateway | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 1 | 0 |  |  | Yes |  | Stages supports Twilio or IpTelx currently. Customer has to partner with these serivces to establish service levels
Message Center Basic | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | Yes |  | Telephony integration requirements . Stages supports Aeonix , Avaya , Twilio , Pure Cloud and Genesys today.
Message Center Unlimited | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | Yes |  | same as above
IVR | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 4 | 0 |  |  | Yes |  | virtual offering only - SIP Trunk provided by Central Station via PBX or oursourced to ISP like OneTel
Backup IVR | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | Yes |  | same
Virtual IVR | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 4 | 0 |  |  | Yes |  | same
NextStage | NA | NA | NA | NA | NA | NA | NA | NA | 16 | 0 | 4 | 6 |  |  | Yes |  | I have concerns offering this going forward , Bruce Weissman was only engineer that knew this configuration process , This information was not passed along to new Dev members in training prior to Bruce departure
CenterStage | NA | NA | NA | NA | NA | NA | NA | NA | 16 | 0 | 4 | 6 |  |  | Yes |  | Self contained IIS/ SQL / connect Stages platform . Use case un 10K accounts
Smartphone Interface | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | No |  | API #2 standard implimentation
ASAP Implementation | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 6 | 0 |  |  | YES |  | TMA relationship required , Setup takes few hours
RapidSOS Integration | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 6 | 0 |  |  | YES |  | Newer Integration , Supported in Stages 2.7.3 ,
ipDirector - Individual IP Address | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | No |  | 1 IP address mapping
ipDirector - Quarter Block | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | No |  | 63 IP addresses, Mapping 1 to 1 or PAT
ipDirector - Half Block | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | No |  | 127 IP addresses , Mapping 1 to 1 or PAT
ipDirector - Full Block | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | No |  | 254 IP addresses , Mapping 1 to 1 or PAT
Backstage Enterprise Monitoring | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 4 | 0 |  |  | YES |  | device monitoring , Don't know difference in line 121
API Gateway Developer | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | YES |  | API Standard, Development allowed against this definiton of the API
API Gateway Runtime | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 2 | 0 |  |  | No |  | API standard , No development against this definition of the API

## SO Template (hidden)
Exhibit B - Project Scope Considerations
|  |  |  | Compiled by: | John Doe
|  |  |  | Compiled with: | Salley Smith
[6 empty] | S | M | L |  | PM | App Cons | Sys Cons | Tech Cons
Question | S | M | L | Answer | Notes |  |  |  | Total | 0 | 0 | 0 | 0
Generic Questions | [5 empty] | 0 | 0 | 0
Do you have an identified project manager to serve as the primary point of contact for all project-related issues? | [5 empty] | 0 | 0 | 0
Have you chosen the main individuals who will participate in User Acceptance Testing (UAT)? | [5 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
SO Core
SO Net New - On Prem (no -add on modules) | [5 empty] | 0 | 0 | 0
Do you need a conversion? | No | Yes | Yes |  |  | 0 | 0 | 0
How many locations do you have? | 1 to 2 | 3 to 4 | 5+ |  |  | 0 | 0 | 0
How many branches will you need setup | 1 to 2 | 3 to 4 | 5+ |  |  | 0 | 0 | 0
All Core Application Features Utilized | No | Yes | Yes |  |  | 0 | 0 | 0
Only AR Tools Being Utilized | Yes | No | No |  |  | 0 | 0 | 0
Net New Conversion | [5 empty] | 0 | 0 | 0
Is there a data conversion required to be faciliated by Perennial consultants? (Y/N) - If No, only generic questions needed | No | Yes | Yes |  |  | 0 | 0 | 0
Do you need Perennial to script data from your csv, access or sql backup into the staging document? | No | Yes | Yes |  |  | 0 | 0 | 0
Do you need more than 4 data passes? | No | No | Yes |  |  | 0 | 0 | 0
Is a data extraction going to be required for Bold group to pull from Clients existing system? | No | No | Yes |  |  | 0 | 0 | 0
Dashboard
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
Forte Integration (EFT) (same for MG)
Do you need multiple merchant accounts for different business entities? | No | Yes | N/A |  |  | 0 | 0 | 0
ADI Integration
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
WeSuite Integration
What QuoteWerks Products are you adding? | N/A license add only | QuoteValet, QuoteWerks integration | N/A |  |  | 0 | 0 | 0
Sebis Integration
SO Modules*
Sedona X Mobile
How many branches do you have? | N/A license add only | only 1 | 2+ |  |  | 0 | 0 | 0
Sedona-X Mobile App - FSU Migration
How many technicians do you have needed to be setup? | 1 to 9 | 10 + | N/A |  |  | 0 | 0 | 0
SalesAutomation
Only need generic questions | N/A license add only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
eForms
Do you need Bold group to configure eForms templates? | N/A license add only | Yes, then requires custom scope | Yes, then requires custom scope |  |  | 0 | 0 | 0
Time and Attendance
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SedonaWeb 2.0
Are you migrating from SedonaWeb 1 to SedonaWeb 2? | No | Yes | N/A |  |  | 0 | 0 | 0
API 2.0 - Full Version
API 1.0 Custom Deveploment work in place? | No | Yes | N/A |  |  | 0 | 0 | 0
Is this being installed in Bold Groups AWS Hosted Enviorment | No | Yes | N/A |  |  | 0 | 0 | 0
API 2.0 - Limited Version
API 1.0 Custom Deveploment work in place? | No | Yes | N/A |  |  | 0 | 0 | 0
Is this being installed in Bold Groups AWS Hosted Enviorment | No | Yes | N/A |  |  | 0 | 0 | 0
Sedona Sync
Do you have a Subject Matter Expert Internally on SedonaOffice Database Tables and SQL? | Yes | No | No |  |  | 0 | 0 | 0
Do you have an assigned admin Internally to activate and modify events in event pack? | Yes | No | No |  |  | 0 | 0 | 0
Do you need events created for multiple branches? | No | No | No |  |  | 0 | 0 | 0
Do you need the service notification event pack in addition to the invoice event pack actived by Bold Group? | No | Yes | Yes |  |  | 0 | 0 | 0
FireNSpec
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SO-Manitou Integration
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SO - Stages Integration
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SO - CMS Integration
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SedonaDocs
Are you hosted or on-prem? | Hosted/On-prem - Does not effect LOE, Information for PM to direct system consultant | N/A | N/A |  |  | 0 | 0 | 0
QuoteWorks Integration
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
Services | [5 empty] | 1 | 1 | 1
BPA - Comprehensive/Focused
How many locations do you have and need a review for? | 1 | 1 | 2+ |  |  | 0 | 0 | 0
Do you need you need a review on the entire application? | No | Yes | Yes |  |  | 0 | 0 | 0
Cloud Migrations
Do you use any of the modules listed (SedonaSync, SedonaWeb, SedonaAPI, Forte Integration, SedonaDashboard) ? | No | Yes | Yes |  |  | 0 | 0 | 0
Do you use any of the third parties listed: Vivid, WeSuite, OPT? | No | Yes | Yes |  |  | 0 | 0 | 0
Upgrades
Do you use any of the modules listed (SedonaSync, SedonaWeb, SedonaAPI, Forte Integration, FSU, SedonaDashboard) ? | No | Yes | Yes |  |  | 0 | 0 | 0
Do you use any of the third parties listed: Vivid, WeSuite, OPT? | No | Yes | Yes |  |  | 0 | 0 | 0
Acqusition Migrations
Do you need these as a seperate branch? | Yes | Yes | No |  |  | 0 | 0 | 0
How many data sources are we importing? | 1 | 2 to 3 | 3+ |  |  | 0 | 0 | 0
Is there a data conversion required to be faciliated by Perennial consultants? (Y/N) - If No, only generic questions needed | Yes | Yes | Yes |  |  | 0 | 0 | 0
Do you need Perennial to script data from your csv, access or sql backup into the staging document? | No | Yes | Yes |  |  | 0 | 0 | 0
Is a data extraction going to be required for Bold group to pull from Clients existing system? | No | No | Yes |  |  | 0 | 0 | 0
Do you use any of the modules listed activated in a test enviorment (SedonaSync, SedonaWeb, SedonaAPI, Forte Integration, FSU, SedonaDashboard) ? | No | No | Yes |  |  | 0 | 0 | 0
Forte Token Import (same for MG)
Do you need porting of CC/ACH Data? | No | Yes | N/A |  |  | 0 | 0 | 0
Do you need multiple merchant accounts for different business entities? | No | Yes | N/A |  |  | 0 | 0 | 0
Reinstall
Do you use any of the modules listed (SedonaSync, SedonaWeb, SedonaAPI, Forte Integration, SedonaDashboard) ? | No | Yes | N/A |  |  | 0 | 0 | 0

## SedonaOffice Survey Questions (hidden)
Exhibit B - Project Scope Considerations
|  |  |  | Compiled by: | Justin DeBaggis
|  |  |  | Compiled with: | Justin. D test Company
[6 empty] | S | M | L |  | PM | App Cons | Sys Cons | Tech Cons
Question | S | M | L | Answer | Notes | 0 | 0 | 0 | Total hours to be input into SFDC | 0 | 0 | 0 | 0
Generic Questions | [5 empty] | 0 | 0 | 0
Do you have an identified project manager to serve as the primary point of contact for all project-related issues? | No | No | N/A |  |  | 0 | 0 | 0
Have you chosen the main individuals who will participate in User Acceptance Testing (UAT)? | Yes | No | N/A |  |  | 0 | 0 | 0
SO Core
SO Net New - On Prem (no -add on modules) | [5 empty] | 0 | 0 | 0
How many locations do you have? | 1 to 2 | 3 to 4 | 5+ |  |  | 0 | 0 | 0
How many branches will you need to setup? | 1 to 2 | 3 to 4 | 5+ |  |  | 0 | 0 | 0
Will all of the application's key functionalities—including AR, AP, Work Orders, Scheduling, General Ledger—be used? | No | Yes | Yes |  |  | 0 | 0 | 0
Will you only be utilizing the Accounts Receivable function in Sedona? | Yes | No | No |  |  | 0 | 0 | 0
Net New Conversion | [5 empty] | 0 | 0 | 0
Is there a data conversion required to be faciliated by Perennial consultants? If yes, what is it? | No | Yes | Yes |  |  | 0 | 0 | 0
How many data sources will need to be converted? | 1 | 2 to 4 | 5+ |  |  | 0 | 0 | 0
What application(s) are you moving from with sources of data required to convert? | Freeform text answer |  |  |  |  | 0 | 0 | 0
For the staging document, do you need Perennial to script data from your csv, access, or SQL backup? | No | Yes | Yes |  |  | 0 | 0 | 0
Do you require more than four data passes? | No | No | Yes |  |  | 0 | 0 | 0
Will Perennial need to perform a data extraction in order to obtain information from the client's current system? | No | No | Yes |  |  | 0 | 0 | 0
Dashboard | [5 empty] | 0 | 0 | 0
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
Forte Integration (EFT) (same for MG) | [5 empty] | 0 | 0 | 0
Are numerous merchant accounts required for various business entities? If yes, how many? | No | Yes | N/A |  |  | 0 | 0 | 0
ADI Integration | [5 empty] | 0 | 0 | 0
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
WeSuite Integration | [5 empty] | 0 | 0 | 0
Only need generic questions | Only need generic questions | Only need generic questions | Only need generic questions |  |  | 0 | 0 | 0
Sebis Integration | [5 empty] | 0 | 0 | 0
Only need generic questions | Only need generic questions | Only need generic questions | Only need generic questions |  |  | 0 | 0 | 0
SO Modules*
Sedona X Mobile | [5 empty] | 0 | 0 | 0
How many branches do you have? | N/A license add only | only 1 | 2+ |  |  | 0 | 0 | 0
Sedona-X Mobile App - FSU Migration | [5 empty] | 0 | 0 | 0
How many technicians are required to be setup? | 1 to 9 | 10 + | N/A |  |  | 0 | 0 | 0
SalesAutomation | [5 empty] | 0 | 0 | 0
Only need generic questions | N/A license add only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
eForms | [5 empty] | 0 | 0 | 0
Do you require BoldGroup to configure eForms templates? | N/A license add only | Yes, then requires custom scope | Yes, then requires custom scope |  |  | 0 | 0 | 0
Time and Attendance | [5 empty] | 0 | 0 | 0
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SedonaWeb 2.0 | [5 empty] | 0 | 0 | 0
Are you migrating from SedonaWeb 1 to SedonaWeb 2? | No | Yes | N/A |  |  | 0 | 0 | 0
API 2.0 - Full Version | [5 empty] | 0 | 0 | 0
Do you have customization built utilizing the SedonaAPI 1.0? | No | Yes | N/A |  |  | 0 | 0 | 0
Is the API being installed in BoldGroup's AWS Hosted Environment? | No | Yes | N/A |  |  | 0 | 0 | 0
API 2.0 - Limited Version | [5 empty] | 0 | 0 | 0
Do you have customization built utilizing the SedonaAPI 1.0? | No | Yes | N/A |  |  | 0 | 0 | 0
Is the SedonaAPI being installed in BoldGroup's AWS Hosted Environment? | No | Yes | N/A |  |  | 0 | 0 | 0
Sedona Sync | [5 empty] | 0 | 0 | 0
Is there an internal Subject Matter Expert on SedonaOffice Database Tables and SQL? | Yes | No | No |  |  | 0 | 0 | 0
Do you have a staff administrator who can add and remove events from the event pack? | Yes | No | No |  |  | 0 | 0 | 0
Do you require the creation of events for various branches? | No | Yes | Yes |  |  | 0 | 0 | 0
Do you also require the Perennial activated service notice event pack in addition to the invoice event pack? | No | Yes | Yes |  |  | 0 | 0 | 0
FireNSpec | [5 empty] | 0 | 0 | 0
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SO-Manitou Integration | [5 empty] | 0 | 0 | 0
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SO - Stages Integration | [5 empty] | 0 | 0 | 0
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SO - CMS Integration | [5 empty] | 0 | 0 | 0
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
SedonaDocs | [5 empty] | 0 | 0 | 0
Are you hosted or on-prem? | Hosted/On-prem - Does not effect LOE, Information for PM to direct system consultant | N/A | N/A |  |  | 0 | 0 | 0
QuoteWorks Integration | [5 empty] | 0 | 0 | 0
Only need generic questions | Generic Questions only | Generic Questions only | Generic Questions only |  |  | 0 | 0 | 0
Services
BPA - Comprehensive/Focused | [5 empty] | 0 | 0 | 0
How many different locations do you need reviews for? | 1 | 2 to 5 | 5+ |  |  | 0 | 0 | 0
Will a review of the entire application be needed? | No | Yes | Yes |  |  | 0 | 0 | 0
Cloud Migrations | [5 empty] | 0 | 0 | 0
Do you use any of the modules listed (SedonaSync, SedonaWeb, SedonaAPI, Forte Integration, SedonaDashboard) ? | No | Yes | Yes |  |  | 0 | 0 | 0
Do you use any of the third parties listed: Vivid, WeSuite, OPT? | No | Yes | Yes |  |  | 0 | 0 | 0
Upgrades | [5 empty] | 0 | 0 | 0
Do you use any of the modules listed (SedonaSync, SedonaWeb, SedonaAPI, Forte Integration, FSU, SedonaDashboard) ? | No | Yes | Yes |  |  | 0 | 0 | 0
Do you use any of the third parties listed: Vivid, WeSuite, OPT? | No | Yes | Yes |  |  | 0 | 0 | 0
Acqusition Migrations | [5 empty] | 0 | 0 | 0
Is there a data conversion required to be faciliated by Perennial consultants? If yes, what is it? | Yes | Yes | Yes |  |  | 0 | 0 | 0
Do you require setting up multiple branches in the database? | No | Yes | Yes |  |  | 0 | 0 | 0
How many data sources are we importing? | 1 | 2 to 3 | 3+ |  |  | 0 | 0 | 0
Where are the data sources coming from? | Freeform answer |  |  |  |  | 0 | 0 | 0
For the staging document, do you need Perennial to script data from your csv, access or SQL backup? | No | Yes | Yes |  |  | 0 | 0 | 0
Will Perennial need to perform a data extraction in order to obtain information from the client's current system? | No | No | Yes |  |  | 0 | 0 | 0
Do you utilize any of the following modules in a test environment: (SedonaSync, SedonaWeb, SedonaAPI, Forte Integration, FSU, SedonaDashboard) ? IF yes, which one(s)? | No | No | Yes |  |  | 0 | 0 | 0
Forte Token Import (same for MG) | [5 empty] | 0 | 0 | 0
Do you require porting of CC/ACH Data? | No | Yes | N/A |  |  | 0 | 0 | 0
Are numerous merchant accounts required for various business entities? If yes, how many? | No | Yes | N/A |  |  | 0 | 0 | 0
Reinstall | [5 empty] | 0 | 0 | 0
Do you use any of the modules listed (SedonaSync, SedonaWeb, SedonaAPI, Forte Integration, SedonaDashboard) ? | No | Yes | N/A |  |  | 0 | 0 | 0

## Managely Survey Question
Exhibit B - Project Scope Considerations
|  |  |  | Compiled by: | Steve Fetherston
|  |  |  | Compiled with: | Mick Jagger
[6 empty] | S | M | L |  | PM | App Cons | Sys Cons | Tech Cons
Question | S | M | L | Answer | Notes | 6 | 4 | 0 | Total hours to be input into SFDC | 0 | 0 | 0 | 0
Generic Questions | [5 empty] | 2 | 0 | 0
Do you have an identified project manager to serve as the primary point of contact for all project-related issues? | Yes | No | N/A | Yes |  | 1 | 0 | 0
Have you chosen the main individuals who will run User Acceptance Testing (UAT)? | Yes | No | N/A | Yes |  | 1 | 0 | 0
Services
BPA - Comprehensive/Focused | [5 empty] | 0 | 0 | 0
How many different locations do you need reviews for? | 1 | Two to Five | 5+ |  |  | 0 | 0 | 0
Will a review of the entire core SedonaOffice application be needed? | No | Yes | Yes |  |  | 0 | 0 | 0
Acqusition Migrations | [5 empty] | 0 | 0 | 0
Do you require data to be imported multiple branches? If yes, how many branches? | Yes | Yes | No, merging into existing Branch |  |  | 0 | 0 | 0
How many data sources are we importing? | 1 | 2 to 3 | 3+ |  |  | 0 | 0 | 0
For the staging document, do you need Perennial to script data from your csv, access or SQL backup? | No | Yes | Yes |  |  | 0 | 0 | 0
Will Perennial need to perform a data extraction in order to obtain information from the client's current system? | No | No | Yes |  |  | 0 | 0 | 0
Forte Token Import (same for MG) | [5 empty] | 0 | 0 | 0
Are numerous merchant accounts required for various business entities? If yes, how many? | No | Yes | Yes |  |  | 0 | 0 | 0
Managely
Net New Managely | [5 empty] | 2 | 2 | 0 |  | 8 | 16 | 0 | 0
Do you require setting up multiple branches in the database? | No | Yes | Yes | No |  | 1 | 0 | 0
How many branches will you need setup? | 1 to 2 | 3 to 4 | 5+ | 1 to 2 |  | 1 | 0 | 0
Are all of the core application features being used? | No | Yes | Yes | Yes |  | 0 | 1 | 0
Will you be using only AR tools? | Yes | No | No | No |  | 0 | 1 | 0
Net New Managely Conversion | [5 empty] | 2 | 2 | 0 |  | 0 | 0 | 0 | 30
Is there a data conversion required to be faciliated by Perennial consultants? If yes, what is it? | No | Yes | Yes | Yes |  | 0 | 1 | 0
How many data sources are we importing? | 1 | 2 to 3 | 3+ | 1 |  | 1 | 0 | 0
For the staging document, do you need Perennial to script data from your csv, access or SQL backup? | No | Yes | Yes | Yes | Yes will need help | 0 | 1 | 0
Will Perennial need to perform a data extraction in order to obtain information from the client's current system? | No | No | Yes | No | Sample notes | 1 | 0 | 0
AB > Managely | [5 empty] | 0 | 0 | 0
How many AlarmBiller databases? | 1 | 1 | 2+ |  |  | 0 | 0 | 0
Do you require data to be converted ouside of just AlarmBiller? | No | No | Yes |  |  | 0 | 0 | 0
Are you planning to use Managely's General Ledger and do you need it set up? | No | Yes | Yes |  |  | 0 | 0 | 0
Do you require a Go-Live Resource following the Managely switchover? | No | Yes | Yes |  |  | 0 | 0 | 0
SO > Managely | [9 empty] | 0 | 0 | 0 | 0
How many SedonaOffice Databases do you have? | [5 empty] | 1 | 1 | 1
How many branches do you have setup in each database? | [5 empty] | 1 | 1 | 1
Do you require data to be converted outside of SedonaOffice? | [5 empty] | 1 | 1 | 1
Are you currently using SedonaOffice for your General ledger? |  | Tool for Sedona to Managely conversion does not currently exist; no answers to these questions as of yet |  |  |  | 1 | 1 | 1
What number of mids have you allocated to Forte Accounts? | [5 empty] | 1 | 1 | 1
Do you currently have any ODBC-connected reports or active SQL jobs running? | [5 empty] | 1 | 1 | 1
Do you have any customization via API? | [5 empty] | 1 | 1 | 1
Are you using any third party services such as Vivid, OPT, WeSuite etc? | [5 empty] | 1 | 1 | 1
Sedona-X | [5 empty] | 0 | 0 | 0
Uses only generic questions | Uses only generic questions | Uses only generic questions | Uses only generic questions |  |  | 0 | 0 | 0
Partner Integrations | [5 empty] | 0 | 0 | 0
Uses only generic questions | [5 empty] | 0 | 0 | 0

## Manitou Survey Questions (hidden)
Exhibit B - Project Scope Considerations
|  |  |  | Compiled by: | John Doe
|  |  |  | Compiled with: | Salley Smith
[6 empty] | S | M | L |  | PM | App Cons | Sys Cons | Tech Cons
Question | S | M | L | Answer | Notes | 0 | 0 | 0 | Total hours to be input into SFDC | 0 | 0 | 0 | 0
Manitou Core | [5 empty] | 0 | 0 | 0
On Prem - Standard Bundle | Known (MKS, DICE, MAS) | Unfamiliar System | IBS or Multiple Sources |  |  | 0 | 0 | 0
Do you require a redundant alarm automation platform? | [5 empty] | 0 | 0 | 0
Is there a data conversion? (Y/N) - If No, no more questions. | [5 empty] | 0 | 0 | 0
What is the Data Source? | [5 empty] | 0 | 0 | 0
On Prem - Business Bundle | Known (MKS, DICE, MAS) | Unfamiliar System | IBS or Multiple Sources |  |  | 0 | 0 | 0
Do you require remote access to your system, automated Email/SMS notifications, and video integration? | [5 empty] | 0 | 0 | 0
Is there a data conversion? (Y/N) - If No, no more questions. | [5 empty] | 0 | 0 | 0
What is the Data Source? | [5 empty] | 0 | 0 | 0
On Prem - Premier Bundle | [5 empty] | 0 | 0 | 0
Do you require everything in the Business package, AND also do GPS or non-traditional alarm monitoring requiring mapping and location data? | [5 empty] | 0 | 0 | 0
Is there a data conversion? (Y/N) - If No, no more questions. | Known (MKS, DICE, MAS) | Unfamiliar System | IBS or Multiple Sources |  |  | 0 | 0 | 0
What is the Data Source? | [5 empty] | 0 | 0 | 0
On Prem - Enterprise Bundle | [5 empty] | 0 | 0 | 0
Would you like a Manitou package with every module we offer? | [5 empty] | 0 | 0 | 0
Is there a data conversion? (Y/N) - If No, no more questions. | Known (MKS, DICE, MAS) | Unfamiliar System | IBS or Multiple Sources |  |  | 0 | 0 | 0
What is the Data Source? | [5 empty] | 0 | 0 | 0
MCS - Standard Bundle | [5 empty] | 0 | 0 | 0
Do you only need the basic alarm automation software in the Cloud? | [5 empty] | 0 | 0 | 0
Is there a data conversion? (Y/N) - If No, no more questions. | Known (MKS, DICE, MAS) | Unfamiliar System | IBS or Multiple Sources |  |  | 0 | 0 | 0
What is the Data Source? | [5 empty] | 0 | 0 | 0
MCS - Business Bundle | [5 empty] | 0 | 0 | 0
Do you require remote access to your system, automated Email/SMS notifications, and video integration? | [5 empty] | 0 | 0 | 0
Is there a data conversion? (Y/N) - If No, no more questions. | Known (MKS, DICE, MAS) | Unfamiliar System | IBS or Multiple Sources |  |  | 0 | 0 | 0
What is the Data Source? | [5 empty] | 0 | 0 | 0
MCS - Premier Bundle | [5 empty] | 0 | 0 | 0
Do you require everything in the Business package, AND also do GPS or non-traditional alarm monitoring requiring mapping and location data? | [5 empty] | 0 | 0 | 0
Is there a data conversion? (Y/N) - If No, no more questions. | Known (MKS, DICE, MAS) | Unfamiliar System | IBS or Multiple Sources |  |  | 0 | 0 | 0
What is the Data Source? | [5 empty] | 0 | 0 | 0
MCS - Enterprise Bundle | [5 empty] | 0 | 0 | 0
Would you like a Manitou package with every module we offer? | [5 empty] | 0 | 0 | 0
Is there a data conversion? (Y/N) - If No, no more questions. | Known (MKS, DICE, MAS) | Unfamiliar System | IBS or Multiple Sources |  |  | 0 | 0 | 0
What is the Data Source? | [5 empty] | 0 | 0 | 0
Manitou Modules
Universal Connector | [5 empty] | 0 | 0 | 0
Do you monitor any non-standard alarm inputs such as Email alerts, SMS alerts, TCP or XML signals? Do you monitor any standard XML signals such as Alarm.com? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Do you monitor any GPS enabled devices that require an alarm location is displayed on a map? | [5 empty] | 0 | 0 | 0
Standard Import Utility | [5 empty] | 0 | 0 | 0
Do you require the ability to upload large batches of customer accounts directly to your system? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Autotext | [5 empty] | 0 | 0 | 0
Do you require automated outbound Email notifications on alarms? How about SMS messages? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
OpenVoice Inbound | [5 empty] | 0 | 0 | 0
Do you require a way for technicians to call into the system to place accounts on test? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
BoldNet Mobile | [5 empty] | 0 | 0 | 0
Do you require remote access to your system for technicians or end users? Do they require a mobile app? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
BoldNet | [5 empty] | 0 | 0 | 0
Do you require remote access to your system for technicians or end users? Do they require a mobile app? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
VCC - (Should be Video Driver) | [5 empty] | 0 | 0 | 0
Do you require video integration with your alarms? Do you have additional video platforms? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Stealth | [5 empty] | 0 | 0 | 0
Do you require a virtual print-out from your receivers, for either troubleshooting signal traffic OR for redundancy purposes for UL? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Advanced Report Writer | [5 empty] | 0 | 0 | 0
Do you need to be able to write your own custom reports? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
OpenVoice Outbound | [5 empty] | 0 | 0 | 0
Do you require outbound IVR calls in response to alarms? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Virtual Operator | [5 empty] | 0 | 0 | 0
Do you require automated outbound Email notifications on alarms? How about SMS messages? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
PBX Cloud | [5 empty] | 0 | 0 | 0
Do you require the ability to auto-dial directly out of Manitou? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
PBX Standard | [5 empty] | 0 | 0 | 0
Do you require the ability to auto-dial directly out of Manitou? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
PBX Enterprise | [5 empty] | 0 | 0 | 0
Do you monitor any TwoWay capable devices? How many concurrent TwoWay calls do you need to manage? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Do you require outbound IVR calls in response to alarms? | [5 empty] | 0 | 0 | 0
Voice Record | [5 empty] | 0 | 0 | 0
Do you require a link in the activity log to your phone systems recording platform? (This requires software via a third party partner) | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Warm Replication | [5 empty] | 0 | 0 | 0
Do you need a redundant system? Do you require UL? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Multi Replication | [5 empty] | 0 | 0 | 0
Do you need a redundant system? Do you require UL? Do you have multiple sites? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
AccessPoint | [5 empty] | 0 | 0 | 0
Do you require an integration with an Access Control System? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Location Services | [5 empty] | 0 | 0 | 0
Do you monitor any GPS enabled devices that require an alarm location is displayed on a map? Do you require the ability to lookup PSAP data for account validation? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
ASAP to PSAP | [5 empty] | 0 | 0 | 0
Do you require the TMA ASAP to PSAP integration | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
BoldTrak (1500 or Unlimited) | [5 empty] | 0 | 0 | 0
Do you monitor any GPS enabled devices that require an alarm location is displayed on a map? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Dealer Billing | [5 empty] | 0 | 0 | 0
Do you require the ability to automatically generate invoices for your Dealers via our Accounting Integrations? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Enhanced Dealer Billing | [5 empty] | 0 | 0 | 0
Do you require Enhanced Dealer Billing with your Accounting Integration? (Pro-rated, Time based or Signal based? (Requires SedonaOffice) | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundany server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Software Developers Kit (MDK) | [5 empty] | 0 | 0 | 0
Do you require our REST API To allow third-party integration into Manitou? For example, Alarm.com Contact and Zone sync with Manitou. | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundany server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Remote FEP | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Training Gym Tier 1 | [5 empty] | 0 | 0 | 0
Do you require a non-production TEST or DEVELOPMENT environment? Do you need to be able to test our API? Do you need to be able to test every component of your production system? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Training Gym Tier 2 | [5 empty] | 0 | 0 | 0
Do you require a non-production TEST or DEVELOPMENT environment? Do you need to be able to test our API? Do you need to be able to test every component of your production system? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Training Gym Tier 3 | [5 empty] | 0 | 0 | 0
Do you require a non-production TEST or DEVELOPMENT environment? Do you need to be able to test our API? Do you need to be able to test every component of your production system? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
XML Receiver Driver | [5 empty] | 0 | 0 | 0
Do you monitor any standard XML signals such as Alarm.com? | [5 empty] | 0 | 0 | 0
Is there an Existing Integration? (To be answered by Sales Rep) | Yes | Yes | No |  |  | 0 | 0 | 0
If Existing Integration, do you need Backup Receiver? | No | Yes | Yes |  |  | 0 | 0 | 0
Monitoring Group | [5 empty] | 0 | 0 | 0
Do you require having multiple alarm queues to separate alarms by region or type? How many total queues are required? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
TwoWayPlus | [5 empty] | 0 | 0 | 0
Do you monitor any TwoWay capable devices? How many concurrent TwoWay calls do you need to manage? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
How many types of devices? | 1 | 1 | 1 |  |  | 0 | 0 | 0
How many two-way lines are being monitored? | 0-4 | 5 to 8 | 8 to 24 |  |  | 0 | 0 | 0
History Server | [5 empty] | 0 | 0 | 0
Do you require a non-production Manitou server in order to lookup History? (This is for customers no longer using Manitou) | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Accounting Integration | [5 empty] | 0 | 0 | 0
Do you require a direct integration with our SedonaOffice or Managely accounting platforms? | [5 empty] | 0 | 0 | 0
Does the module need to be installed on a redundant server? | No = No additional hours | Yes = +50% hours per server |  |  |  | 0 | 0 | 0
Cloud Receiver | [5 empty] | 0 | 0 | 0
Are you looking to get rid of your on premise receivers and move all of your alarm traffic to a Cloud hosted platform? | [5 empty] | 0 | 0 | 0
Number of Accounts monitored? | 0-1000 | 1001-5000 | 5001-20,000 |  |  | 0 | 0 | 0

## AM Project Descriptions (hidden)
OAF Instructions
- everything under the 5hr threshold either on App or tech consultant, which doesn’t require a SOW, will have a brief “project” or “scope” description on the OAF, so that PS knows what the work is for
- everything above that threshold, and therefore requiring a SOW, will have same description on the SOW under section 8 “special requirements/terms” until we get EC to make a text field available under section 4 “scope”
Manitou Core
Net New - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Net New Manitou w/ Migration | This SOW covers the itemized services required for the delivery of training and services related to the migration from external data sources to Manitou based on the source database available. Estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. Does not include history data converted. | Copy and paste into special Terms field
Number of Sources: 1 or less
Data Passes: 2 test; 1 Go-Live
Client to provide Bold Group a copy of their current database backup in .BAK (SQL Database) file format for conversion into Manitou.
|  | Net New Manitou w/ No Migration | This SOW covers the itemized services required for the delivery of training and services related to the onboarding of Manitou with no data conversion included, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
No Conversion Included: Client will be manually entering data into Manitou
Migrations - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Phoenix to Manitou Migration | This SOW covers the itemized services required for the delivery of training and services related to the migration from Phoenix to Manitou, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | SIMS to Manitou Migration | This SOW covers the itemized services required for the delivery of training and services related to the migration from SIMS to Manitou, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Manitou On-Prem to Manitou Cloud | This SOW covers the itemized services required for the delivery of training and services related to the upgrade from Manitou On-Prem to Manitou Cloud, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
Add-on Module Sale - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Standard Import Utility | This SOW covers the itemized services required for the delivery of training and or services related to the Standard Import Utility, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Autotext | This SOW covers the itemized services required for the delivery of training and or services related to the AutoText, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field along with which provider the customer has selected
|  | OpenVoice Inbound | This SOW covers the itemized services required for the delivery of training and or services related to the OpenVoice Inbound, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | BoldNet Mobile | This SOW covers the itemized services required for the delivery of training and or services related to the BoldNet Mobile, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | BoldNet | This SOW covers the itemized services required for the delivery of training and or services related to the BoldNet, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | VCC - (Should be Video Driver) | This SOW covers the itemized services required for the delivery of training and or services related to the Video Control Center, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field and include specifics on which video driver(s) are being implemented
|  | Bold NotifyMe | This SOW covers the itemized services required for the delivery of training and or services related to the Bold NotifyMe, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | High Availability | This SOW covers the itemized services required for the delivery of training and or services related to the High Availablilty, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Stealth | This SOW covers the itemized services required for the delivery of training and or services related to the Stealth, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Advanced Report Writer | This SOW covers the itemized services required for the delivery of training and or services related to the Advanced Report Writer, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Manitou Cloud Services (not sure what this is) | This SOW covers the itemized services required for the delivery of training and or services related to the Manitou Cloud Services, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | MCS - SaaS | This SOW covers the itemized services required for the delivery of training and or services related to the MS SaaS, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | OpenVoice Outbound | This SOW covers the itemized services required for the delivery of training and or services related to the OpenVoice Outbound, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Business Continuity Services | This SOW covers the itemized services required for the delivery of training and or services related to the Business Continuity Services, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Cloud Receiver Backup | This SOW covers the itemized services required for the delivery of training and or services related to the Cloud Receiver Backup, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Virtual Operator | This SOW covers the itemized services required for the delivery of training and or services related to the Virtual Operator, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | PBX Cloud | This SOW covers the itemized services required for the delivery of training and or services related to the PBX Cloud, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | PBX Standard | This SOW covers the itemized services required for the delivery of training and or services related to the PBX Standard, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | PBX Enterprise | This SOW covers the itemized services required for the delivery of training and or services related to the PBX Enterprise, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Voice Record | This SOW covers the itemized services required for the delivery of training and or services related to the Voice Record, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Warm Replication | This SOW covers the itemized services required for the delivery of training and or services related to the Warm Replication, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Multi Replication | This SOW covers the itemized services required for the delivery of training and or services related to the Multi Replication, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | AccessPoint | This SOW covers the itemized services required for the delivery of training and or services related to the AccessPoint, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Location Services | This SOW covers the itemized services required for the delivery of training and or services related to the Location Services, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | ASAP to PSAP | This SOW covers the itemized services required for the delivery of training and or services related to ASAP to PSAP, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field and include any additional details regarding TMA and PSAP provider
|  | BoldTrak (1500 or Unlimited) | This SOW covers the itemized services required for the delivery of training and or services related to the BoldTrak, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Dealer Billing | This SOW covers the itemized services required for the delivery of training and or services related to the Dealer Billing, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Enhanced Dealer Billing | This SOW covers the itemized services required for the delivery of training and or services related to the Enhanced Dealer Billing, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Software Developers Kit (MDK) | This SOW covers the itemized services required for the delivery of training and or services related to the Software Developers Kit, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Remote FEP | This SOW covers the itemized services required for the delivery of training and or services related to the Remote FEP, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | SoloProtect | This SOW covers the itemized services required for the delivery of training and or services related to the Solo Protect, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Training Gym Tier 1 | This SOW covers the itemized services required for the delivery of training and or services related to the Training Gym Tier 1, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Training Gym Tier 2 | This SOW covers the itemized services required for the delivery of training and or services related to the Training Gym Tier 2, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Training Gym Tier 3 | This SOW covers the itemized services required for the delivery of training and or services related to the Training Gym Tier 3, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field along with details on modules to be installed
|  | XML Receiver Driver | This SOW covers the itemized services required for the delivery of training and or services related to the XML Receiver Driver estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Monitoring Group | This SOW covers the itemized services required for the delivery of training and or services related to the Monitoring Group, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | TwoWayPlus | This SOW covers the itemized services required for the delivery of training and or services related to the TwoWayPlus, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | TwoWayPlus - InstantConnect | This SOW covers the itemized services required for the delivery of training and or services related to the TwoWayPlus InstantConnect, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | History Server | This SOW covers the itemized services required for the delivery of training and or services related to the History Server, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Accounting Integration | This SOW covers the itemized services required for the delivery of training and or services related to the Accounting Integration, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field along with which accounting package will be integrated
|  | Cloud Receiver | This SOW covers the itemized services required for the delivery of training and or services related to the Cloud Receiver, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
Service Only
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Application Training Only |  | Write in explaination of services to be performed
|  | Technical Consulting |  | Write in explaination of services to be performed
|  | Development |  | Write in explaination of services to be performed
|  | Project Management |  | Write in explaination of services to be performed
|  | System Consulting |  | Write in explaination of services to be performed

## BM Project Descriptions
OAF Instructions
- everything under the 5hr threshold either on App or tech consultant, which doesn’t require a SOW, will have a brief “project” or “scope” description on the OAF, so that PS knows what the work is for
- everything above that threshold, and therefore requiring a SOW, will have same description on the SOW under section 8 “special requirements/terms” until we get EC to make a text field available under section 4 “scope”
Managely
Net New - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Net New Managely w/ Migration | This SOW covers the itemized services required for the delivery of training and services related to the migration from external data sources to Managely based on available fields on the "Managely Data Conversion Services" list, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | 1. Override number of sources if required and increase respective hours based on pricing matrix
|  |  | Number of Sources: 2 or less | 2. If we are extracting data add additional languade from service labeled Data Extraction below
|  |  | Data Passes: 2 test; 1 Go-Live | 3. Copy and paste into special Terms field
Client is extracting data from existing system and populating the staging document.
|  | Net New Managely w/ No Migration | This SOW covers the itemized services required for the delivery of training and services related to the onboarding of Managely with no data conversion included, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
No Conversion Included: Client will be manually entering data into Managely
Migrations - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | AB to Managely Migration | This SOW covers the itemized services required for the delivery of training and services related to the migration from AlarmBiller to Managely, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field | This Agreement covers the itemized services required for the delivery of training and services related to the migration from AlarmBiller to Managely, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this Agreement documented scope.
|  | SO to Managely | This SOW covers the itemized services required for the delivery of training and services related to the migration from SedonaOffice to Managely, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | Essentials to Pro | This SOW covers the itemized services required for the delivery of training and services related to the upgrade from Managely Essentials to Managely Pro, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
Add-on Module Sale - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Sedona-X Mobile App | This SOW covers the itemized services required for the delivery of training or services related to the implementation of Sedona-X Mobile for Managely, estimated based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
Service Only
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Forte Token Porting | This SOW covers the itemized services required for the delivery of porting tokens (once provided to Forte) into Managely as identified on the spreadsheet provided by Forte and verified by the Client. Estimates based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
Client has reached out to Forte to start the process of communicating with there existing processing vendor.
|  | eForms Template Creation | This SOW covers the itemized services required for the delivery of services related to creation of eForms templates for Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. Client has provided all eForm templates for Bold consultant to review and provide a level of effort. | 1. Enter in the number of templates to be created
2. Copy and paste into special Terms field
Total Number of eForm Templates to be created:
|  | Data Extraction | Bold Group to provide data extraction from client provided existing system backup (via SQL, MS Access, etc) and format in their data migration staging document | 1. Rep must verify/scope with PMO and verify it can be accomplished and LOE
2. Copy and paste into special Terms field
|  | Application Training Only | This covers the itemized services required for the delivery of training related to the Project, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the training areas identified by the Client. | Copy and paste into special Terms field
SedonaOffice
Net New - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Net New SedonaOffice - On-Prem and Hosted | Using Custom SOW (legacy Matthaeus built SOW) outside of application and needs pre-approval from Tammy and Josh for each instance.
Migrations - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | SedonaOffice On-Prem to Hosted Migration | This SOW covers the itemized services required for the delivery of training and or services related to a migration from the Client's SedonaOffice on-premise install to Bold's AWS communal hosted environment, estimated based on system requirements provided by Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | 1. Rep to add existing modules and bold group integrations
|  |  | Existing Modules and integrations to be installed: | 2. Copy and paste into special Terms field
|  | SedonaOffice Hosted to On-Prem Migration | This SOW covers the itemized services required for the delivery of training and or services related to a migration from Bold's AWS communal hosted environment to the Client's SedonaOffice on-premise install to , estimated based on system requirements provided by Client wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | 1. Rep to add existing modules and bold group integrations
|  |  | Existing Modules and integrations to be installed: | 2. Copy and paste into special Terms field
|  | SedonaFSU to Sedona-X Migration | This SOW covers the itemized services required for the delivery of training and or services related to the migration from SedonaFSU to Sedona-X Mobile, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | SedonaWeb 1 to SedonaWeb 2 | This SOW covers the itemized services required for the delivery of training and or services related to the migration from SedonaWeb 1.0 to SedonaWeb 2.0, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
Add-on Module Sale - Services w/ Products
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | SedonaWeb 2 | This SOW covers the itemized services required for the delivery of training and or services related to the SedonaWeb 2.0, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. SedonaAPI 2.0 has been installed and activation of SedonaWeb 2 will be configured. | Copy and paste into special Terms field
|  | Sedona-X | This SOW covers the itemized services required for the delivery of training and or services related to the implementation of Sedona-X , estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. SedonaAPI 2.0 has been installed to support the implementation. | Copy and paste into special Terms field
|  | SedonaAPI 2.0 | This SOW covers the itemized services required for the delivery of training and or services related to the implementation of SedonaAPI 2.0, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | SedonaAPI 2.0 and Sedona-X | This SOW covers the itemized services required for the delivery of training and or services related to the implementation of Sedona-X and SedonaAPI 2.0 , estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | SedonaAPI 2.0 and SedonaWeb 2 | This SOW covers the itemized services required for the delivery of training and or services related to the SedonaWeb 2.0 and SedonaAPI 2.0, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | SalesAutomation and eForms | This SOW covers the itemized services required for the delivery of training and or services related to the implementation of SalesAutomation and eForms, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. SedonaAPI 2.0 has been installed to support the implementation. | Copy and paste into special Terms field
|  | SalesAutomation, eForms and API 2.0 | This SOW covers the itemized services required for the delivery of training and or services related to the implementation of SalesAutomation, eForms, and configuration of the API, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | SedonaDocs | This SOW covers the itemized services required for the delivery of training and or services related to the implementation of SedonaDocs, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
|  | SedonaSync | This SOW covers the itemized services required for the delivery of training and or services related to the SedonaSync Implementation, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. The license will connect to one SedonaOffice database and have 1 client user for an admin to access. | Copy and paste into special Terms field (If custom events are being created please refer to services only SedonaSync Event Creation and add lanauge on details of events being created
|  | SedonaOffice and Manitou Integration | This SOW covers the itemized services required for the delivery of training and or services related to the implementation of SedonaOffice and Manitou integration, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. The client has purchased purchased all necessary licensed applications and meets minimum version compatibilty for alarm monitoring and business management solutions. | Copy and paste into special Terms field
Service Only
|  | Product | Notes Section (Added to SOW Special Terms) | Instructions for rep
|  | Server Reinstall | Clients Existing Modules: | Rep to add existing modules and bold group integrations
|  | eForms Template Creation | This SOW covers the itemized services required for the delivery of services related to creation of eForms templates for Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. Client has provided all eForm templates for Bold consultant to review and provide a level of effort. | Enter in the number of templates to be created
Total Number of eForm Templates to be created:
|  | SedonaSync Event Creation | This covers the itemized services required for the delivery of training and services related the creation of a custom SedonaSync Event, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the training areas identified by the Client. | 1. Rep to enter in # of branches required for event (this will double LOE as requires creation of two events)
|  |  | # of events: | 2. Rep to enter details of each event being created
Description of each event:
|  | Data Extraction | Bold Group to provide data extraction from client provided existing system backup (via SQL, MS Access, etc) and format in their data migration staging document | 1. Rep must verify/scope with PMO and verify it can be accomplished and LOE
2. Copy and paste into special Terms field
|  | Application Training Only | This covers the itemized services required for the delivery of training related to the Project, estimated based on system requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the training areas identified by the Client. | Copy and paste into special Terms field
|  | Forte Token Porting | This SOW covers the itemized services required for the delivery of porting tokens (once provided to Forte) into Managely as identified on the spreadsheet provided by Forte and verified by the Client. Estimates based on requirements provided by the Client, wherein specified Bold Group resources will be assigned to provide specifically the services in this SOW documented scope. | Copy and paste into special Terms field
Client has reached out to Forte to start the process of communicating with there existing processing vendor.